## Sheet1
Name | Cost (Days) | Progress | Remaining Days | Area | Feature | Notes
Jack N. | 1 | 100% | 0 | Front end | Chat Log | Chat log now exists
Jack N. | 1 | 100% | 0 | Front end | Chat Log | Messages can now be added to chat
Jack N. | 1 | 100% | 0 | Front end | Chat Log | User name can be set and now shows up in chat
Nikolai | 1 | 100% | 0 | Server | Serving Files | Serving index html file
Nikolai | 1 | 100% | 0 | Server | Serving files | Experimenting with ways to serve other files in frontend directory
Jack N. | 1 | 100% | 0 | Front end | Game Canvas | Added canvas, got text rendering working
Nikolai | 1 | 100% | 0 | Server | Serving Files | Experimenting with ways to serve files in frontend directory
Jack N. | 1 | 100% | 0 | Front end | Game Canvas | Canvas now has functioning update loop
Jack N. | 1 | 100% | 0 | Front end | Game Canvas | Players can now move by clicking on the screen
Domingo | 1 | 100% | 9 | Frontend | UI | Added CSS to everything in order to make the website usable by human beings
Nikolai | 1 | 100% | 0 | Server | Socket Server | Setting up socket server
Jack N. | 1 | 50% | 2 | Front end | Camera | Camera follows player if they move to the side of screen
Nikolai | 1 | 100% | 0 | Server | Sending Data | Sending jsons to the server instead of strings
Jack N. | 1 | 50% | 1 | Front end | Camera | Fixed players moving incorrectly when the camera moves
Nikolai | 1 | 100% | 0 | Server | Player Sync | Players now see each other on screen
Domingo | 3 | 100% | 0 | Frontend | Sliced Image Scaling | Added function to make images able to scale using "slices". Ultimately makes bigger images look less pixelated overall by only increasing the size of certain slices and keeping others the same
Nikolai | 1 | 100% | 0 | Functional Specification | Document | Created Func Spec doc
Jack N. | 1 | 100% | 0 | Front end | Camera | Camera now zooms, hits borders, and follows player based on distance from center, rather than approaching edges
Nikolai | 0.5 | 100% | 0 | Server | Serving Files | Streamlined code and making it more readable
Jack N. | 1 | 20% | 5 | Front end | Background | Got images working
Nikolai | 0.5 | 100% | 0 | Server | Client Identification | Gave each client a uid to help when signaling other clients when a specific client disconnects
Jack N. | 1 | 30% | 4 | Front end | Background | Images can now be tiled, assembles background based on an array of tiles
Nikolai | 1 | 100% | 0 | Server | Sending Messages | Figuring out how to send data other than strings
Jack N. | 1 | 50% | 3 | Front end | Background | Began building level editor, selecting tiles and declaring map size functional
Nikolai | 1 | 100% | 0 | Server | Username Verification | Checks that the username a client is trying to use is not explicit or already taken
Jack N. | 1 | 60% | 2 | Front end | Background | Level editor can now place tiles, exports map
Jack N. | 1 | 80% | 1 | Front end | Background | Level editor can now import strings and convert them into maps within the editor
Alex Knotwell | 3 | 10000% | 0 | Backend | Chat Filter
Alex Knotwell | 1 | 10000% | 0 | Backend | Username Filter | Bounces invalid username
Alex Knotwell | 2 | 10000% | 0 | Documents | Power Automate excel form
Alex Knotwell | 1 | 100% |  | Backend | AWS | Created AWS EC2 Instance
Alex Knotwell | 3 |  | 20 | Backend | AWS | Moved Backend and Frontend to Instance
Nikolai | 1 | 100% | 0 | Server | Proximity Chat | Made it so messages are only received by those near the sender
Alex Knotwell | 2 | 20% |  | Backend | HTTPS | Started reaserching and converting backend to using 443 port
Added canvas, got text rendering working
Alex Knotwell | 3 | 40% |  | Backend | HTTPS | Installed cerbot and fully converted website to using port 443 and 80.
Alex Knotwell | 2 | 60% |  | Backend | Https | Bought domain and used it to get certification, completed SSL handshake with certification
Alex Knotwell | 4 | 100% | 0 | Backend | Daemon File | FIxed systemD file so that website has 100% uptime.
Alex Knotwell | 3 | 20% |  | Frontend | New Username Input | Revamped Old Username input element and changed it from a div to a true input
Alex Knotwell | 2 | 50% |  | Frontend | New Username Input | New Button that responds to hover and implements JS function
Alex Knotwell | 3 | 75% |  | Frontend | New Chat Input | New CSS style and changed element type to input instead of div.
Jack N. | 3 | 100% | -2 | Frontend | Background | Autotiling is now fully functional
Nikolai | 1 | 100% | 0 | Minigames | Board class | class that handles game boards
Jack N. | 13 | 50% |  | Frontend | Image Atlases | Despite immense effort, it does not work for some unholy reason
Nikolai | 1 | 100% | 0 | Minigames | Adding methods to board class | new methods for manipulating board class
Jack N. | 6 | 50% |  | Front end | Image flipping | Ran into the same issue as image atlases, just handling flipped images as seperate images for now
Nikolai | 1 | 100% | 0 | Minigames | Game class | handles minigames
Jack N. | 6 | 100% |  | Front end | Props | Props now exist in the world, can be scaled, etc, and renders behind other props in a way that it creates a 2.5d effect
Nikolai | 1 | 100% | 0 | Minigames | Card game class | Class that handles card games
Jack N. | 2 | 100% | 0 | Front end | Collisons | Props now have collisions
Nikolai | 1 | 100% | 0 | Minigames | TicTacToe test | functional tictactoe game using game and board classes
Jack N. | 2 | 100% | 0 | Front end | Abyss | A parallax background now shows up, will be implemented to create more convincing map boundaries
Nikolai | 1 | 100% | 0 | Minigames | Debugging tictactoe | worked issues
Nikolai | 1 | 100% | 0 | Minigames | Game Props | props in the world which display a prompt to play when near
Nikolai | 1 | 100% | 0 | Minigames | Game Menu | Menu for join ing and creating rooms for minigames
Nikolai | 1 | 100% | 0 | Minigames | Game Menu | Making the window display when the player interacts with the game prop
Nikolai | 0.5 | 100% | 0 | Minigames | Game Menu | Closing the window
Nikolai | 1 | 100% | 0 | Minigames | Buttons | Buttons for the menu
Nikolai | 1 | 100% | 0 | Minigames | Game Menu | Debugging
Nikolai | 1 | 100% | 0 | Minigames | Game Menu | Adjusted scaling for menu
Nikolai | 1 | 100% | 0 | Minigames | Room Creation | Ability to make game rooms and leave them
Nikolai | 1 | 100% | 0 | Minigames | Join Codes | Created textbox for join codes
Nikolai | 1 | 100% | 0 | Minigames | Join Codes | Taking the input and send to the sever
Nikolai | 1 | 100% | 0 | Minigames | Join Codes | Debugging
Alex Knotwell | 1 | 100% |  | Backend | Frontend Code on AWS | Fixed front end code to run on secure web sockets instead of normal ws
Jack Nieman | 6 | 100% | 0 | Image Manipulation | Sprite Flipping | Implemented sprite flipping, player cosmetics no longer require separate sprites for flipped images
Nikolai | 1 | 100% | 0 | Minigames | Join Codes | Fully debugged
Jack Nieman | 4 | 100% | 0 | Image Manipulation | HSV Recoloring | Added HSV recoloring
Nikolai | 1 | 100% | 0 | Minigames | Room Creation | Fully finished and debugged joining and leaving rooms
Jack Nieman | 3 | 100% | 0 | Abyss | Collisions | Abyss now stops players from walking off into the void
Nikolai | 1 | 100% | 0 | Minigames | Games | Adding documentation
Jack Nieman | 5 | 100% | 0 | Clean Up | Restyling Site | New color palette, general touchups to CSS and HTML
Nikolai | 1 | 100% | 0 | Minigames | Room Creation | Added the option to make private or public game room
Jack Nieman | 0.5 | 100% | 0 | Clean Up | Pop-up shifting whole page | Username pop-up window is now fixed and won't shift the whole page
Nikolai | 0.5 | 100% | 0 | Minigames | Game Menu | Fixed improper scaling of buttons
Jack Nieman | 1 | 100% | 0 | Clean Up | Invisible Props | Props will no longer be invisible if they take too long to load
Nikolai | 0.5 | 100% | 0 | Minigames | Game Menu | Fixed bug that made input box for join codes disapear
Jack Nieman | 0.5 | 100% | 0 | Clean Up | Fixed no name disconnect error | Disconnects will only inform clients if the disconnected client had a username
Nikolai | 0.5 | 100% | 0 | Minigames | Playing a Game | Made it so the creator of the room can start the game when there are enough players
Jack Nieman | 3 | 50% | 4 | Reconnecting | Reconnection to the websocket | Players now reconnect to the websocket upon disconnection
Nikolai | 0.5 | 100% | 0 | Minigames | Changing Room Privacy | Fixed improper scaling of buttons
Jack Nieman | 1 | 100% | 0 | Sprites | Redrawn Cliffs | Cliffs now show the ground underneath
Nikolai | 1 | 100% | 0 | Minigames | Playing a Game | Made it so the creator of the room can start the game when there are enough players
Jack Nieman | 5 | 100% | 0 | Optimization | Tilemap | Now only draws the tile map when it changes, only drawing the tiles that are in view then.
Nikolai | 2 | 100% | 0 | Minigames | Playing a Game | Making it so the tic tac toe board displays
Nikolai | 1 | 100% | 0 | Minigames | Position Updates | Increased speed of server updates as well as flipping the direction the player is facing
Nikolai | 1 | 100% | 0 | Minigames | Playing a Game | Player is able to click the board and add an X or O
Nikolai | 1 | 100% | 0 | Minigames | Playing a Game | The move a player makes is now sent to the other player
Nikolai | 1 | 100% | 0 | Minigames | Playing a Game | Game now detects when a player has won
Nikolai | 1 | 100% | 0 | Minigames | Playing a Game | When a player wins a win message appears
Nikolai | 1 | 100% | 0 | Minigames | Rematching | Rematch button appears on win screen
Nikolai | 1 | 100% | 0 | Minigames | Playing a Game | Removed instances of hardcoding for tic tac toe
Nikolai | 1 | 100% | 0 | Minigames | Rematching | Detects when all players hit the rematch button
Nikolai | 1 | 100% | 0 | Minigames | Rematching | Rematching now starts a new game
Nikolai | 1 | 100% | 0 | Minigames | Rematching | You can now play on a rematched game
Nikolai | 1 | 100% | 0 | Minigames | Leaving Rooms | Server sends a kick command to the opponent when their opponent leavs in the middle of a match
Nikolai | 1 | 100% | 0 | Minigames | Leaving Rooms | Now kicks opponent out of game if you leave during a match
Nikolai | 1 | 100% | 0 | Minigames | Uno | Started making uno a game
Nikolai | 1 | 100% | 0 | Minigames | Tic Tac Toe | Changed the tic tac toe game prop sprite
Nikolai | 1 | 100% | 0 | Minigames | Tic Tac Toe | Added collision to the tic tac toe game prop
Nikolai | 1 | 100% | 0 | Functional Spec | Adding to Repo | Added specs to repo